AI Agent IAM

Implementation Roadmap

Phased Plan for Building Enterprise Identity & Access

Management for AI Agents

February 11, 2026

# Overview

This roadmap sequences the implementation of an enterprise Identity and Access Management (IAM) framework for AI agents. Each phase builds on the previous one, ensuring that at every phase boundary the organization has a usable, incrementally safer system. The plan is structured around dependencies, risk reduction, and incremental value delivery.

The full program spans approximately 22 weeks across 7 phases (including Phase 0), with opportunities for parallel execution between certain phases.

# Timeline Overview

| Phase | Focus Area | Timeline | Dependencies |
| --- | --- | --- | --- |
| Phase 0 | Agent Identity & Registry | Weeks 1–4 | None (foundation) |
| Phase 1 | Scoped Delegation & Permission Boundaries | Weeks 3–7 | Phase 0 |
| Phase 2 | Audit Trail Infrastructure | Weeks 5–10 | Phase 0 |
| Phase 3 | Access Control Policy Engine | Weeks 8–13 | Phases 1 & 2 |
| Phase 4 | Consent & Attestation Framework | Weeks 11–16 | Phase 3 |
| Phase 5 | Lifecycle Management & Automation | Weeks 14–18 | Phases 3 & 4 |
| Phase 6 | Anomaly Detection & Investigation | Weeks 16–22 | Phase 2 (matured data) |

# Phase 0: Agent Identity & Registry

⏱ Weeks 1–4

Why this order: Everything else depends on agents being identifiable entities. You cannot audit, scope, or revoke what you cannot identify.

## Deliverables

- Agent Identity Schema — Define the data model for agent identities: agent_id, owner_user_id, agent_type, model_version, purpose, created_at, lifecycle_state (active / suspended / revoked).

- Agent Registry Service — A central catalog where every agent instance is registered. This is the source of truth for “what agents exist and who owns them.”

- Credential Issuance — Integrate with your IdP to issue short-lived tokens (OAuth2 client credentials or service principal tokens) tied to the agent identity. Establish token TTL policy (e.g., 15–60 minutes) and refresh flow.

- User-Agent Binding — Ensure every agent is linked to a delegating user at registration time. No orphan agents.

## Key Decisions

- Will you extend your existing IdP (Entra ID, Okta, etc.) or build a sidecar registry?

- Token format: JWT with custom claims, or opaque tokens with introspection?

- How do agents authenticate to refresh tokens (mTLS, client secret rotation, workload identity)?

Exit Criteria: You can create an agent identity, issue it a short-lived token, look it up in the registry, and see who owns it.

# Phase 1: Scoped Delegation & Permission Boundaries

⏱ Weeks 3–7 (overlaps with Phase 0)

Why this order: Once agents have identities, you need to constrain what those identities can do. This is your primary preventive control.

## Deliverables

- Token Exchange Flow — Implement RFC 8693 token exchange (or an OBO variant) so that when a user delegates to an agent, a downscoped token is produced carrying both the user’s and agent’s identity.

- Permission Boundary Definitions — Define agent permission boundaries per agent type. These are the ceilings — the maximum scope any agent of that type can hold, regardless of the user’s entitlements.

- Scope Intersection Logic — Build the enforcement logic: effective_permissions = user_grants ∩ agent_requested_scopes ∩ boundary_policy. This runs at token issuance time.

- Privilege Escalation Guards — Validation that rejects any token exchange request where the agent asks for more than the user has.

## Key Decisions

- Where does scope intersection happen — in the IdP, an authorization service, or a token minting service?

- Granularity: are scopes coarse (read / write / admin) or fine-grained (per-resource)?

- How do you version permission boundaries as agent capabilities evolve?

Exit Criteria: An agent receives a token that provably cannot exceed its boundary or the user’s grants. Attempts to escalate are rejected.

# Phase 2: Audit Trail Infrastructure

⏱ Weeks 5–10 (can run in parallel with Phase 1)

Why this order: Before you open up more agent capabilities or allow wider deployment, you need visibility. The audit trail is your detective control and the backbone for investigation, compliance, and anomaly detection later.

## Deliverables

- Audit Event Schema — Formalize the log schema: timestamp, agent_id, delegating_user_id, action, resource, input_context, outcome, session_id / trace_id, policy_decision.

- Instrumentation Layer — Add audit emission at every enforcement point (API gateway, service mesh sidecar, or application middleware). Every agent action emits a structured event.

- Immutable Log Store — Set up append-only storage (WORM-configured object store, SIEM ingestion, or a dedicated audit database with immutability guarantees).

- Correlation / Session Linking — Ensure all actions within a single agent task share a trace_id so you can reconstruct the full sequence during investigation.

- Basic Search & Query — Build or configure a query interface over audit logs (by user, agent, time range, action type, resource).

## Key Decisions

- Storage: dedicated audit lake vs. existing SIEM (Splunk, Sentinel, Elastic)?

- Retention period and compliance requirements (SOC 2, GDPR, industry-specific)?

- How to handle PII sanitization in input_context (the prompt that triggered the action)?

Exit Criteria: Every agent action produces an immutable, searchable audit event. You can reconstruct a full agent session from trace IDs.

# Phase 3: Access Control Policy Engine

⏱ Weeks 8–13

Why this order: With identity, delegation, and audit in place, you now layer on the fine-grained policy logic — the “brain” that makes real-time allow/deny decisions.

## Deliverables

- Policy Engine Selection & Deployment — Stand up a centralized policy engine (OPA/Rego, Cedar, or a custom engine). All enforcement points call this engine for authorization decisions.

- Action Tiering Model — Implement the 4-tier classification: Tier 0 (read-only, auto-allow), Tier 1 (low-risk writes, allow with logging), Tier 2 (sensitive, require human approval), Tier 3 (privileged, blocked for agents).

- Resource-Level Policies — Write policies for your initial agent types (e.g., “code assistant agent can read repos but not merge to main,” “email agent can draft but not send to external domains”).

- Contextual Policy Inputs — Feed context into policy decisions: time of day, user online/offline status, network location, task metadata.

- Human-in-the-Loop Approval Workflow — Build the Tier 2 approval flow: agent requests action → system pauses → user gets notification → user approves/denies → agent proceeds or aborts.

## Key Decisions

- Policy authoring: who writes policies — security team, platform team, or self-service by agent developers?

- Approval UX: how does the human-in-the-loop notification reach the user (email, Slack, mobile push)?

- Latency budget: policy evaluation must be fast enough not to degrade agent performance.

Exit Criteria: Agent actions are evaluated against policies in real time. Tier 2 actions correctly pause for human approval. Tier 3 actions are blocked.

# Phase 4: Consent & Attestation Framework

⏱ Weeks 11–16

Why this order: With the runtime controls working, you now build the governance layer that ensures access stays appropriate over time.

## Deliverables

- Consent Grant Flow — When a user first enables an agent, present a consent screen listing the permissions being granted. Store the grant with timestamp, scope, and user acknowledgment.

- Access Review Dashboard (User-Facing) — A UI showing: all agents acting on the user’s behalf, permissions each agent holds, last-used timestamps per permission, and a Revoke button for immediate deprovisioning.

- Periodic Attestation Engine — Automated recertification campaigns (e.g., quarterly). Users receive a task to review each agent’s access and confirm or revoke. Expired / unattested access is auto-suspended.

- Manager/Admin Attestation — For agents with sensitive scopes, add a second-party review step (the user’s manager or a security delegate).

- Drift Detection — Continuously compare actual agent permissions against the last-attested baseline. Alert on drift.

## Key Decisions

- Attestation cadence: quarterly, monthly, or event-driven (e.g., on role change)?

- What happens on attestation expiry: suspend immediately or grace period?

- How to avoid “rubber-stamping” — can you surface usage data to make attestation decisions informed?

Exit Criteria: Users can see and manage their agents’ access. Attestation campaigns run on schedule. Unattested access is auto-suspended.

# Phase 5: Lifecycle Management & Automation

⏱ Weeks 14–18 (can partially overlap with Phase 4)

Why this order: Now you automate the operational plumbing so the system sustains itself without manual intervention.

## Deliverables

- Automated Provisioning — When a user enables an agent in a product, the identity + delegation + consent grant is created automatically.

- Cascading Suspension — If a user account is locked/suspended (from HR feed or IdP event), all their agents are immediately suspended. Wire this to your IdP’s event stream (SCIM, CAEP, or webhook).

- Real-Time Revocation — Ensure enforcement points can handle immediate revocation (token revocation list, introspection endpoint, or CAEP event).

- Offboarding Cleanup — When a user leaves the organization, automatically deprovision all their agents, scrub cached credentials, and archive audit logs.

- Role Change Re-Evaluation — When a user’s role/department changes, trigger re-evaluation of all their agent permission boundaries. Auto-downscope or flag for review.

## Key Decisions

- Event source: SCIM push, IdP webhooks, HR system integration?

- How fast must cascading suspension propagate (seconds? minutes?)?

- Archive vs. delete policy for departed users’ agent data?

Exit Criteria: Agent lifecycle events are fully automated. User offboarding triggers complete agent cleanup. Role changes trigger permission re-evaluation.

# Phase 6: Anomaly Detection & Advanced Investigation

⏱ Weeks 16–22

Why this order: This is the capstone — it requires a mature audit trail and enough historical data to establish baselines.

## Deliverables

- Behavioral Baselines — Establish per-agent-type and per-user behavioral profiles (typical actions, volumes, time patterns, resource access patterns).

- Anomaly Detection Rules — Implement detection for: agent accessing resources outside its historical pattern, unusual volume of actions (potential runaway agent), actions outside normal hours, repeated authorization denials (potential probing).

- Alert & Escalation Pipeline — Route anomaly alerts to the security team with enriched context (the agent’s identity, the user, the suspicious actions, the audit trail).

- Investigation Toolkit — Build or enhance the forensic interface: full session replay, timeline visualization, comparison against similar agents’ behavior, one-click suspension from the investigation view.

- Feedback Loop — Investigation outcomes feed back into policy tuning and anomaly model refinement.

## Key Decisions

- Rule-based vs. ML-based anomaly detection (start rule-based, graduate to ML)?

- Alert fatigue mitigation: severity scoring, suppression logic?

- Integration with existing SOC / SIEM workflows?

Exit Criteria: Anomalous agent behavior triggers alerts. Investigators can reconstruct and analyze full agent sessions. Findings feed policy improvements.

# Dependency Map

The following illustrates the sequencing dependencies between phases:

Phase 0: Agent Identity & Registry

│

├─▶ Phase 1: Scoped Delegation & Permission Boundaries

│

├─▶ Phase 2: Audit Trail Infrastructure

│       │

│       ├─▶ Phase 3: Access Control Policy Engine

│       │       │

│       │       ├─▶ Phase 4: Consent & Attestation

│       │       │       │

│       │       │       ├─▶ Phase 5: Lifecycle Automation

│       │       │

│       └─▶ Phase 6: Anomaly Detection (needs audit data maturity)

Phases 1 and 2 can overlap (weeks 3–10 run in parallel tracks). Phases 4 and 5 can also partially overlap. Phase 6 should start only after Phase 2 has been in production long enough to accumulate meaningful data.

# Recommended Team Structure

| Stream | Phases | Skills Needed |
| --- | --- | --- |
| Identity & Auth | 0, 1, 5 | IdP engineering, OAuth/OIDC, SCIM |
| Platform / Policy | 3, 4 | Policy-as-code (OPA/Cedar), UX for consent flows |
| Observability & Security | 2, 6 | SIEM/logging infrastructure, detection engineering |

# Quick Wins to Start Immediately

While Phase 0 is being built, the following can be executed in parallel:

- Inventory existing agents — Catalog every AI agent currently operating in your environment, who deployed them, and what access they have today. This becomes your migration backlog.

- Draft the action tiering model — Classify your organization’s APIs and operations into the 4 tiers. This is a policy exercise that does not require code.

- Evaluate policy engines — Run a proof-of-concept with OPA or Cedar against a sample set of agent scenarios.

# Closing Note

This sequencing ensures that at every phase boundary, you have a usable, incrementally safer system — you do not have to wait until Phase 6 to get value. Each phase delivers standalone security improvements while laying the groundwork for the next.

The plan provides defense in depth: preventive controls (scoped delegation, permission boundaries), detective controls (audit logs, anomaly detection), and corrective controls (revocation, attestation-driven cleanup).